## Development Doc
KEY INITIATIVE #1:
Sr | Subject | Current status | Remarks
1 | Planning and initial data gathering
2 | Assess existing database systems (MCSI) and ensure compatibility with the new “SalesPulse” solution.
3 | Create project plans and agree upon general details with concerned departments.
KEY INITIATIVE #1:
Sr | Subject | Current status | Remarks
3 | Implement Sell In module, integrating existing sales data. (Sell IN & Customer Returns) | Phase 1
5 | Develop One Time Stock on Hand (SOH) input interface and tracking logic. (HO & CO) | Phase 1
Develop Regular Stock on Hand (SOH) input interface and tracking logic. (HO & CO)
2 | Module to update /maintain customer masterdata for HO/Cust code. CRUD | Phase 1
4 | Create Sell Out module with Excel upload/download functionality and SOH and feature. (HO & CO) | Phase 1
Establish forecasting module to facilitate accurate monthly sales planning.
General Details Module. Aggregates data from previous modules, capturing expected vs. actual sell-out and dynamically calculating SOH (expected SOH).
1 | User access control: Brand, Customer, Category based | Phase 1
6 | Module for SKU Mapping between MECL & Customers | Phase 1
Promotional Method Module
8 | Notes: Reports will be discussed later stage
7 | Customer upload format mapping module | Phase 1
9 | Dashboard /KPIS/ At a glance reports
1- User Access Control
Sr | Subject | Current status | Remarks
1 | Brand - Customer - Category based
i. Access for a specific Brand and Customer only
ii. Access to an entire brand
2 | Saperate User creation Page
i. SP_Users Table
ii. New user cration and vlidation front and backend
3 | Access management page
i. Page to add / remove access for a user
2-Module Customer masterdata, HO/Cust code Mapping. CRUD
Sr | Subject | Current status | Remarks
1 | Create/Add HO/Cust code
i. 2 tables one for HO and One for Cust. Codes with Unique IDs
ii. One main mapping tables that will contain the relations
| iii. Define Upload/inputsLevel at this point for later inputs |  | HO-Level/Cust-code level
iv. SOHUploadBasis & SellOutUploadbasis. Define if "Transectional" or "Accumilative"
Front End
i. Option to add a new HO
ii. Option to select an HO to add a Cust. Code to it.
iii. Reuse the same UI as RFT category add (IF posible with minimal changes)
Risk-Assesment of Level change
i. Impact on SOH/Sell-out/Reports e.t.c
3-Implement Sell In module, integrating existing sales data. (Sell IN & Customer Returns)
Sr | Subject | Current status | Remarks
Saperate Sell-in For SALES-PULSE for required Cust.codes (TABLE)
i.Issue ( missing data after last schedule in current MSCI)
ii. One hour window for API to run
iii. 3 times a day API schedule Current(12:15 PM)(4:30 PM)(09:00 AM)
iv. All columns included in this table as in MCSI SAP/ Same all in general Report + value Per item(may change per line for same article)
v. Sell-in start date for that HO code from date of one time SOH (Delete the rest)(LINKED TO MODULE 5)
vi. One line of this customer must exist in SOH (MODULE 5) table to start fetch sell-in. (Its Customer onboarding logic)
Sell_in = Sell_in-Returns
General Sell-In report
i. Dynamic filters for all columns (Real-time)
ii. Excel export with filters
iii. Cust.code mapping with HO code for filter and export (LINKED TO MODULE 1)
Checks
i. No sell-out (MODULE 4) if SKU is not in Sell-in
ii.
4-Create Sell Out module with Excel upload/download functionality. (HO & CO)
Sr | Subject | Current status | Remarks
1 | (Add Sell-in Page)Sell-Out Uploading FRONT END:
i. User will select Brand
ii. HO/Cust selection based on the level defined in MODULE 2.2.3
iii.Selelct Unique SKU from a list (Based on MODULE 3.1 and MODULE 6)
a) CatName, Sku, Cust SKU, SOH
b)Append zero SOH items to the end for improved UX
iv. Create a Doucument with SPNUM containing Unique SKUs
v. Option to input Date,SKU(MECL/CUST) MODULE 6.1.2, SOH and Sellout Qty (CatName just for show)
vi. If SKU mapping is missing while upload take user to MODULE 6 prefill the missing skus to add maping
vii. Option to add atachments/View/Delete
viii. Option to download excel
a) This will be locked to the selected SKUs
b) only take upload after download to prevent old files confusion
ix. Option to hide SOH Column (To be discussed)
x. At the Sell out compare with Soh for that specific transection Date.
xi. Add abutton for DRAFT-SAVE (Incse missing any data)
2 | Pending approval Page
i. Page to show list of all Uploads of sell-out
ii. Filters for all columns
iii. Brand, HO/Cust code based MODULE 2.2.3 , Upload-DATE, Data date range
iv. Sell-out statuses
a) Draft (still editable) (Deleteable) --------------------------------------(To be discussed)
b) Pending approval Brand Admin (Locked to edit)
c) Pending approval Finance Admin (Locked to edit) --------------------------------------(To be discussed)
d) Approved
i. Used in reporting after approval
e) Rejected (Editable) (on save back to C)
3 | WorkFlow of Sell-out to approval
i.We need an admin for Brand (Brand Admin)
ii. Then admin for all brands (Finance Admin)
iii. MODULE 4.2.4
Frontend Pending approval
i. Brand, HO/Cust code based MODULE 2.2.3 , SP-Num, SP-DATE, Data date range, est.Values
ii. Approve button, Reject Button, Remarks
iii. Bulk approve
iv. Filters
4 | Negative Scnarios
i. Sell-out is more then SOH. Then What ????
a) report on Dashboard show Brand, Custome/Ho code, Sp-num(Clickable)
b) Highlite issue line on SP_list page in Module 4.2.1
ii. Customer missed an article while making manual selection
a) give option to add an article using sp-Num
iii. Customer added a wrong item
a) Let him remove the item
5 | Bulk Upload "Cust-Format"
i. Only the customer with a format set will show aoption to upload with that format directly MODULE 7.1
ii. This will branch from Module 4.1.2
6 | Checks:
i.OPTIONAL: In Cust-Format upload First let user download the format he set so he can copy paste the date in it to minimize issues on format mismatch
ii. Show a confirmation to user of the data uploaded and make him scroll to the end for confirmation.
iii. Define wather to use MEC or Cust Skus in the table brforehand MODULE 6
iv. If SKU mapping doesnot exist show error to users and stop upload.
v. Add the Cust-SKU to SKU-Mapping if provided in sell-out upload (MODULE 6.1.5)
7 | Upload Sell-out page (DIRECT UPLOAD)
i. Select Brand and customer
ii. Download template
iii. Template will contain column headers on Sheet1
iv. Sku Mapping on Sheet 2
v. User can copy paste between sheets or add manually with spell checking enabled (If posible)
5-One Time SOH input and tracking. (HO & Cust)
Sr | Subject | Current status | Remarks
1 | SOH column (either as in sellin table or make a saperate table )
i. Initially user will upload SOH with format like HO-Code/Cust-Code, Article, SOH and Date
ii. This number will be used as initial startting point and will be asumed as current SOH for any customer
Frontend
i. Selection of Brand, Customer
ii. Date selection as Start Date
ii. Upload the file
iii. Review the uploaded file and save to reflect
6-Module for SKU Mapping between MECL & Customers
Sr | Subject | Current status | Remarks
1 | Create a table for MEC x Customer sku names
i. Will contain list of columns like MEC-Sku, Cust-Sku, CustID, ID
ii. Support CRUD operations to ADD, Remove EDIT and DELETE Mapings
iii. Used at prefilling data for MODULE 4.1.6 restiction
iv. Supports excel upload for bulk Company X Cust sku mapping
v. Supports auto asignment of Cust Sku to company SKU if non-existing mapping and Available in Sell-out upload
Checks:
i. Canot add same sku twice for one cust
ii. Show a confirmation to user of the data uploaded and make him scroll to the end for confirmation.
iii. Stop operations for Module 4 when this page is open to prevent wrong sku uploads
iv.
Frontend:
i. A page to add/Map Sku
7-Customer upload format mapping module
Sr | Subject | Current status | Remarks
1 | Create a table for CustomerFormatsMaping
i. Will contain list of columns as exactly as provided by customer format/dump/excel
ii. Format type "Company-Format" or "Cust-Format" defined at MODULE 2.1.4
iii. Customers selection
Frontend:
i. customer selection beore format
ii. Format upload
iii. Listed of already existing formats for all
iv. CRUD options
8- Reports
Sr | Subject | Current status | Remarks
1 | Customer Stock Aging report
i. Will contain list of columns like : Customer, Brand, Article, Description, days( buckets e.g 30+), SOH Avg Age,Oldest Lot, Newest Lot, Total In, Total Out, Last Sell-out, Last Movement (Type e.g SELL-in/Sell-out/Return e.t.c)
ii. Filters for all columns
2 | Sales Pulse - General Report
i. Will contain list of columns like: Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value Price (assumed), Sell-out, SOH (as of To)
ii. Filter for each column
iii. Most important date window filter will provide results beetween the filtered date for (Sell-in/out/SOH)
3 | Overselling Report
i. Will contain list of columns Like : Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value Price (assumed), Sell-out, Current SOH
iii. Will only contain Negative SOH article lines based on Article->Customer->Brand
iv. Filters for all columns
v. At a glance data cards for totals
4 | Daily Report
i. Will contain list of columns Like : Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value(acurate for the day), Sell-out, Sell-out, Value, Current SOH (of the day)
ii. This will contain line item for each day for each customer
iii. Filters are mendetory to run this report
iv. Main/required filter : Brand, Cust
v. Optional filter e.g From date, To Date, Article, CatName, CatDesc E.T.C
9- Dashboard /KPIs / At-a glance reports
Sr | Subject | Current status | Remarks
1 | Inventory Days at customer
i. Average days stock stays in store before being sold
2 | Chanel Performance
Sales per customer
3 | Sell-through rate (70% - 80%)
Sell-out + (sell-in - openng Stock)
4 | Sell-out Growth
Change vs Latest month/quarter year
5 | Sell-out value
Revenue sold to Customer
6 | Stock-in-trade / Channel Inventory
How much stock is sitting with the customer
7 | Sales Velocity VS sell-in
=> | Top/ Bottom velocity Skus
High sell-in + High Velocity (Strong Demand)
High sell-in + Low Velocity (Overstock)
Low sell-in + High Velocity (Stockout)
Low sell-in + Low Velocity (Weak Demand)
8 | Reorder Reminder: If customer has low stock but his sell-in is High Velocity
9 | Sell-out History (Using AI to show demand)
10 | Upsell opportunity =?
11 | Lost Sales opportunity = ? IMP
12 | Order Matrix (At a glance)
Project requirements
| Subject | Current status | Remarks
| SQL Server Integration | Tested | Existing MCSI database
| Excel (PANDAS) Integration for Sell Out reports download and upload. | Tested | Development required
| Python (Flask) for backend | Tested | Installed
| Pandas Library | Tested | Installed
| Secure data management tools | Tested | To ensure data protection compliance
Project Time lines
| Subject | ECD | Remarks
| Modules development | 2025-07-01
| All Module QA readiness | 2025-07-01
| Domain/Hosting & security clearance | 2025-08-01 | Subjected to AFG (will apply by end of July
| Testing and bug fixes | 2025-08-01
| User training | 2025-08-01
| Production deployment | 2025-08-01

## Wireframes
|  |  | Sell_in-Returns-Sellout |  |  |  | Article selection |  |  |  | SP11222
Date | Mec-Sku | Cust-Sku | SOH | Sell-out | CATName | Date | Mec-Sku | Cust-Sku | SOH | Sell-out | Date | Mec-Sku | Cust-Sku | Sell-out
2025-07-15 | 1 | [5 empty] | 1 |  |  |  |  | 1
2025-07-15 | 1 | [5 empty] | 2 |  |  |  |  | 2
| 3 | [5 empty] | 3 |  |  |  |  | 3
| 4 | [5 empty] | 4 |  |  |  |  | 4
| 5 | [5 empty] | 5 |  |  |  |  | 5
| 6 | [5 empty] | 6
| 7 | [5 empty] | 7 |  |  |  | Download excel |  | Locked and 100% matching |  | Attachments
| 8 | [5 empty] | 8 |  |  |  | Upload excel |  |  |  | Atc 1 | View | Delete
| 9 | [5 empty] | 9 | [7 empty] | Atc 2 | View | Delete
| 10 | [5 empty] | 10 | [7 empty] | Atc 3 | View | Delete
| 11 | [5 empty] | 11
| 12 | [5 empty] | 12
| 13 | [5 empty] | 13
| 14 | [5 empty] | 14 | [7 empty] | Save
| 15 | [5 empty] | 15
| 16 | [5 empty] | 16
| 17 | [5 empty] | 17

## Adil-Bhi Related (hidden)
Issues
i.Issue ( missing data after last schedule in current MSCI)
ii. Return Qty missing in MCSI report