## Development Doc
Initial Phase
Sr | Subject | Current status | Remarks
1 | Planning and initial data gathering | Completed
2 | Assess existing database systems (MCSI) and ensure compatibility with the new “Sales Pulse” solution. | Completed
3 | Create project plans and agree upon general details with concerned departments. | Completed
KEY INITIATIVE #1:
Sr | Subject | Current status | Remarks
3 | Implement Sell In module, integrating existing sales data. (Sell IN & Customer Returns) | Phase 1 | Completed
5 | Develop One Time Stock on Hand (SOH) input interface and tracking logic. (HO & CO) | Phase 1 | Completed
| Develop Regular Stock on Hand (SOH) input interface and tracking logic. (HO & CO) | Phase 2 | Phase 2
2 | Module to update /maintain customer master data for HO/Cust code. CRUD | Phase 1 | Completed
4 | Create Sell Out module with Excel upload/download functionality and SOH and feature. (HO & CO) | Phase 1 | Completed
| Establish forecasting module to facilitate accurate monthly sales planning. | Phase 2 | Phase 2
| General Details Module. Aggregates data from previous modules, capturing expected vs. actual sell-out and dynamically calculating SOH (expected SOH). | Phase 1 | Completed
1 | User access control: Brand, Customer, Category based | Phase 1 | Completed
6 | Module for SKU Mapping between MECL & Customers | Phase 1 | Completed
| Promotional Method Module | Phase 2 | Phase 2
8 | Reports
7 | Customer upload format mapping module | Phase 1 | Completed
9 | Dashboard /KPIS/ At a glance reports | Phase 1 | Completed
1- User Access Control
Sr | Subject | Current status | Remarks
1 | Brand - Customer - Category based | Completed
| i. Access for a specific Brand and Customer only | Completed
| ii. Access to an entire brand | Completed
2 | Separate User creation Page | Completed
| i. SP_Users Table | Completed
| ii. New user creation and validation front and backend | Completed
3 | Access management page | Completed
| i. Page to add / remove access for a user | Completed
4 | User List page | Phase 2
5 | User Audit log Page | Phase 2
2-Module Customer master data, HO/Cust code Mapping. CRUD
Sr | Subject | Current status | Remarks
1 | Create/Add HO/Cust code
| Customers management page (Statuses and activation logic) (Active, Inactive, Sell-in Hibernateing, Sell-out Hibernating, Dead E.t.C) | Completed
| i. 2 tables one for HO and One for Cust. Codes with Unique IDs | Completed
| ii. One main mapping tables that will contain the relations | Completed
| iii. Define Upload/inputs Level at this point for later inputs | Completed | HO-Level/Cust-code level
| iv. SOHUploadBasis & SellOutUploadbasis. Define if "Transactional" or "Accumulative" | Completed
| Customers Contact Book Page | Phase 2
| Front End | Completed
| i. Option to add a new HO | Completed
| ii. Option to select an HO to add a Cust. Code to it. | Completed
| iii. Reuse the same UI as RFT category add (IF possible with minimal changes) | Completed
Risk-Assessment of Level change
i. Impact on SOH/Sell-out/Reports etc.
3-Implement Sell In module, integrating existing sales data. (Sell IN & Customer Returns)
Sr | Subject | Current status | Remarks
Separate Sell-in For SALES-PULSE for required Cust. Codes (TABLE)
| I. Issue ( missing data after last schedule in current MSCI) | Completed | To be checked with Adil (IT)
| ii. One hour window for API to run | Completed
| iii. 3 times a day API schedule Current(12:15 PM)(4:30 PM)(09:00 AM) | Completed
| iv. All columns included in this table as in MCSI SAP/ Same all in general Report + value Per item(may change per line for same article) | Completed
| v. Sell-in start date for that HO code from date of one time SOH (Delete the rest)(LINKED TO MODULE 5) | Completed
| vi. One line of this customer must exist in SOH (MODULE 5) table to start fetch sell-in. (Its Customer onboarding logic) | Completed
| Sell_in = Sell_in-Returns | Completed
General Sell-In report
| i. Dynamic filters for all columns (Real-time) | Completed
| ii. Excel export with filters | Completed
| iii. Cust. Code mapping with HO code for filter and export (LINKED TO MODULE 1) | Completed
Checks
| i. No sell-out (MODULE 4) if SKU is not in Sell-in | Completed
4-Create Sell Out module with Excel upload/download functionality. (HO & CO)
Sr | Subject | Current status | Remarks
1 | UPLOAD SELL-OUT page --> FRONT END: | Phase 2
| i. User will select Brand | Completed
| ii. HO/Cust selection based on the level defined in MODULE 2.2.3 | Completed
| iii. Option to add attachments/View/Delete | Completed
| iv. Option to download excel | Completed
| a) This will be locked to the selected SKUs | Completed
| b) only take upload after download to prevent old files confusion | Completed
| v. Option to hide SOH Column (To be discussed) | Completed
| vi. At the Sell out compare with Soh for that specific transection Date. | Completed
| vii. Sell-out template should also include SKU if they have SOH only and no sell-in | Completed
| viii. SOH check along with sell-in check when sell-out uploading toi ensure SKU exists | Completed
| ix. Add a button for DRAFT-SAVE (Incse missing any data) | Completed
2 | Pending approval Page | Completed
| i. Page to show list of all Uploads of sell-out | Completed
| ii. Filters for all columns | Completed
| iii. Brand, HO/Cust code based MODULE 2.2.3 , Upload-DATE, Data date range | Completed
| iv. Sell-out statuses | Completed
| a) Draft (still editable) (Delete able) --------------------------------------(To be discussed) | Completed
| b) Pending approval Brand Admin (Locked to edit) | Completed
| c) Pending approval Finance Admin (Locked to edit) --------------------------------------(To be discussed) | Completed
| d) Approved | Completed
| i. Used in reporting after approval | Completed
| e) Rejected (Editable) (on save back to C) | Completed
3 | Workflow of Sell-out to approval | Completed
| I. An admin for Brand (Brand Admin) that will approve sell-out | Completed
| ii. Then admin for all brands (Finance Admin) - can see and approve all sell-out and has overall read-access | Completed
iii. MODULE 4.2.4
| Frontend Pending approval | Completed
| i. Brand, HO/Cust code based MODULE 2.2.3 , SP-Num, SP-DATE, Data date range, est.Values | Completed
| ii. Approve button, Reject Button, Remarks | Completed
| iii. Bulk approve | Completed
| iv. Filters | Completed
4 | Negative Scenarios
| i. Sell-out is more then SOH. (we can allow it to go for approval) | Completed
| a) report on Dashboard show Brand, Customer/Ho code, Sp-num(Clickable) | Completed
| b) Highlight issue line on SP_list page in Module 4.2.1 | Completed
5 | Bulk Upload "Cust-Format"
| i. Only the customer with a format set will show aoption to upload with that format directly MODULE 7.1 | Phase 2
| ii. This will branch from Module 4.1.2 | Phase 2
6 | Checks:
| I. OPTIONAL: In Cust-Format upload First let user download the format he set so he can copy paste the date in it to minimize issues on format mismatch | Phase 2
| ii. Show a confirmation to user of the data uploaded and make him scroll to the end for confirmation. | Phase 2
| iii. Define wather to use MEC or Cust Skus in the table beforehand MODULE 6 | Phase 2
| v. Add the Cust-SKU to SKU-Mapping if provided in sell-out upload (MODULE 6.1.5) | Phase 2
7 | Upload Sell-out page (DIRECT UPLOAD) | Completed
| i. Select Brand and customer | Completed
| ii. Download template | Completed
| iii. Template will contain column headers on Sheet1 | Completed
| iv. Sku Mapping on Sheet 2 | Completed
| v. User can copy paste between sheets or add manually with spell checking enabled (If possible) | Completed
5-One Time SOH input and tracking. (HO & Cust)
Sr | Subject | Current status | Remarks
1 | SOH column (either as in selling table or make a separate table ) | Completed
| i. Initially user will upload SOH with format like HO-Code/Cust-Code, Article, SOH and Date | Completed
| ii. This number will be used as initial starting point and will be assumed as current SOH for any customer | Completed
| Allow per brand SOH so one customer can receive Initial SOH multiple times for multiple brands | Completed
| If need to change the SOH of already uploaded brand of a customer then select SnapShot Type "Superceed" | Completed
Frontend
| i. Selection of Customer, SOH date, SnapShot Type | Completed
| ii. Downlaod the template file | Completed
| ii. Upload the file | Completed
Checksd and Negative scnarios
i. Cannot upload negative SOH
ii. Cannot upload for future date
iii. Must have correct Brand name spelling in file
6-Module for SKU Mapping between MECL & Customers
Sr | Subject | Current status | Remarks
1 | Create a table for MEC x Customer sku names | Completed
| i. Will contain list of columns like MEC-Sku, Cust-Sku, CustID, ID | Completed
| ii. Support CRUD operations to ADD, Remove EDIT and DELETE Mappings | Completed
| iii. Used at prefilling data for MODULE 4.1.6 restriction | Completed
| iv. Supports excel upload for bulk Company X Cust sku mapping | Completed
| v. Supports auto assignment of Cust Sku to company SKU if non-existing mapping and Available in Sell-out upload | Completed
Checks:
i. Cannot add same sku twice for one cust
ii. Show a confirmation to user of the data uploaded and make him scroll to the end for confirmation.
iii. Stop operations for Module 4 when this page is open to prevent wrong sku uploads
Frontend:
| i. A page to add/Map Sku | Completed
7-Customer upload format mapping module
Sr | Subject | Current status | Remarks
1 | Create a table for CustomerFormatsMaping
| i. Will contain list of columns as exactly as provided by customer format/dump/excel | Testing- Phase 2
| ii. Format type "Company-Format" or "Cust-Format" defined at MODULE 2.1.4 | Testing- Phase 2
| iii. Customers selection | Testing- Phase 2
Frontend:
| i. customer selection before format | Completed
| ii. Format upload | Completed
| iii. Listed of already existing formats for all | Completed
| iv. CRUD options | Completed
8- Reports
Sr | Subject | Current status | Remarks
ALL REPORTS SHOULD ONLY GIVE CALCULATIONS RESULTS STARTING FROM GO-Live/INITAIL SOH DATE for selected /brand and customer
1 | Customer Stock Aging report
| i. Will contain list of columns like : Customer, Brand, Article, Description, days( buckets e.g 30+), SOH Avg Age, Oldest Lot, Newest Lot, Total In, Total Out, Last Sell-out, Last Movement (Type e.g. SELL-in/Sell-out/Return etc.) | Completed
| ii. Filters for all columns | Completed
2 | Sales Pulse - General Report
| i. Will contain list of columns like: Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value Price (assumed), Sell-out, SOH (as of To) | Completed
| ii. Filter for each column | Completed
| iii. Most important date window filter will provide results between the filtered date for (Sell-in/out/SOH) | Completed
| iv. Alllow export to excel | Completed
3 | Overselling Report
| i. Will contain list of columns Like : Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value Price (assumed), Sell-out, Current SOH | Completed
| iii. Will only contain Negative SOH article lines based on Article->Customer->Brand | Completed
| iv. Filters for all columns | Completed
| v. At a glance data cards for totals | Completed
4 | Daily Report
| i. Will contain list of columns Like : Sr., Brand, Customer, Category (Name — Desc), Cust-SKU, MEC-SKU, Sell-in (Qty), Sell-in Value(accurate for the day), Sell-out, Sell-out, Value, Current SOH (of the day) | Completed
| ii. This will contain line item for each day for each customer | Completed
| iii. Filters are mandatory to run this report | Completed
| iv. Main/required filter : Brand, Cust | Completed
| v. Optional filter e.g From date, To Date, Article, Cat Name, CatDesc E.T.C | Completed
9- Dashboard /KPIs / At-a glance reports
Sr | Subject | Current status | Remarks
1 | Inventory Days at customer
| i. Average days stock stays in store before being sold | Planned - phase 2
2 | Chanel Performance
| Sales per customer | Completed
3 | Sell-through rate (70% - 80%)
| Sell-out + (sell-in - opening Stock) | Completed
4 | Sell-out Growth
| Change vs Latest month/quarter year | Completed
5 | Sell-out value
| Revenue sold to Customer | Completed
6 | Stock-in-trade / Channel Inventory
| How much stock is sitting with the customer | Completed
7 | Sales Velocity VS sell-in
=> | Sell-In to Velocity Balance Index (Index > 1 = Pushing more than selling , Index < 1 = Selling faster than supplying.) | Planned - phase 2
=> | Top/ Bottom velocity Skus | Planned - phase 2
=> | High sell-in + High Velocity (Strong Demand) | Planned - phase 2
=> | High sell-in + Low Velocity (Overstock) | Planned - phase 2
=> | Low sell-in + High Velocity (Stockout) | Planned - phase 2
=> | Low sell-in + Low Velocity (Weak Demand) | Planned - phase 2
AI Enabled Analytics
8 | Reorder Reminder: If customer has low stock but his sell-in is High Velocity | Planned - phase 2
9 | Sell-out History (Using AI to show demand) | Planned - phase 2
11 | Lost Sales opportunity | Planned - phase 2
12 | Order Matrix (At a glance) | Completed
Project requirements
| Subject | Current status | Remarks
| SQL Server Integration | Tested | Existing MCSI database
| Excel (PANDAS) Integration for Sell Out reports download and upload. | Tested | Development required
| Python (Flask) for backend | Tested | Installed
| Pandas Library | Tested | Installed
| Secure data management tools | Tested | To ensure data protection compliance
Project Time lines
| Subject | ECD | Remarks
| Modules development | 2025-07-01
| All Module QA readiness | 2025-07-01
| Domain/Hosting & security clearance | 2025-08-01 | Subjected to AFG (will apply by end of July
| Testing and bug fixes | 2025-08-01
| User training | 2025-08-01
| Production deployment | 2025-08-01

## Velocity
Product | Sell-In Units | Sell-Out Units | Stores | Time (Weeks) | Sales Velocity (Units/Store/Week) | Sell-In Achievement % | Weeks of Supply | Sell-In vs Velocity Index | Status
Product A | 1200 | 900 | 30 | 4 | 7.5 | 120 | 5.3333 | 1.3333 | Overstock Risk
Product B | 800 | 500 | 20 | 4 | 6.25 | 80 | 6.4 | 1.6 | Overstock Risk
Product C | 400 | 600 | 15 | 4 | 10 | 40 | 2.6667 | 0.66667 | Stockout Risk

## Wireframes
|  |  | Sell_in-Returns-Sellout |  |  |  | Article selection |  |  |  | SP11222
Date | Mec-Sku | Cust-Sku | SOH | Sell-out | CATName | Date | Mec-Sku | Cust-Sku | SOH | Sell-out | Date | Mec-Sku | Cust-Sku | Sell-out
2025-07-15 | 1 | [5 empty] | 1 |  |  |  |  | 1
2025-07-15 | 1 | [5 empty] | 2 |  |  |  |  | 2
| 3 | [5 empty] | 3 |  |  |  |  | 3
| 4 | [5 empty] | 4 |  |  |  |  | 4
| 5 | [5 empty] | 5 |  |  |  |  | 5
| 6 | [5 empty] | 6
| 7 | [5 empty] | 7 |  |  |  | Download excel |  | Locked and 100% matching |  | Attachments
| 8 | [5 empty] | 8 |  |  |  | Upload excel |  |  |  | Atc 1 | View | Delete
| 9 | [5 empty] | 9 | [7 empty] | Atc 2 | View | Delete
| 10 | [5 empty] | 10 | [7 empty] | Atc 3 | View | Delete
| 11 | [5 empty] | 11
| 12 | [5 empty] | 12
| 13 | [5 empty] | 13
| 14 | [5 empty] | 14 | [7 empty] | Save
| 15 | [5 empty] | 15
| 16 | [5 empty] | 16
| 17 | [5 empty] | 17

## Adil-Bhi Related (hidden)
Issues
i.Issue ( missing data after last schedule in current MSCI)
ii. Return Qty missing in MCSI report