PROJECT MANDATE

| PROJECT NAME: | “SalesPulse” Sell-out Monitoring & Forecasting |
| --- | --- |
| PROJECT OWNER: | Khalid Patel / Arsalan |
| PROJECT MANAGER: | Abdul Wahab |
| PROJECT DEVELOPER | Bilal Zafar |
| PROJECT TIMEFRAME: | JULY – AUG 2025 |

| PROJECT OBJECTIVES |  |
| --- | --- |
| The objective of the “SalesPulse” system is to automate the tracking and forecasting of distribution (Sell In) and sales (Sell Out) across B2B Customers. This system will provide visibility of customer SOH, enable accurate forecasting, and streamline SELL in & SELL out management processes. |  |
| PROJECT KEY FEATURES |  |
| - Automated inventory tracking, significantly reducing manual input errors. - Visibility into customer stock on hand. - Efficient forecasting capabilities for Sell Out planning. - Excel integration for easy customer data input and reporting. |  |
| KEY RELATIONSHIPS AND DEPENDENCIES |  |
| - Project Handling - Supply Chain Department - Finance Department - Sales and Marketing Department - Program Developer - IT Support |  |
| KPI/Enhancements - Reduce manual errors in tracking - Improve forecasting accuracy. - Sell in and out data accessible to all stakeholders. - Enhance customer engagement and accuracy of stock data via simplified Excel templates. | TARGET |
| KEY ACTIONS |  |

| KEY INITIATIVE #1: Planning and initial data gathering |  |  |  |
| --- | --- | --- | --- |
| ITEM | WHAT | WHO | WHEN |
| 1. | Assess existing database systems (MCSI) and ensure compatibility with the new “SalesPulse” solution. | Abdul Wahab | 01-06-25 |
| 2. | Create project plans and agree upon general details with concerned departments. | Abdul Wahab |  |

| KEY INITIATIVE #2: Development of Core Modules |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ITEM |  | WHAT |  | WHO |  | WHEN |
| 1. |  | Implement Sell In module, integrating existing sales data. |  | Bilal |  | 01-07-25 |
| 2. |  | Develop Stock on Hand (SOH) input interface and tracking logic. |  | Bilal |  | 15-07-25 |
| 3. |  | Create Sell Out module with Excel upload/download functionality and SOH and feature. |  | Bilal |  | 20-07-25 |
| 3. |  | Establish forecasting module to facilitate accurate monthly sales planning. |  | Bilal |  | 20-07-25 |
| 4. |  | General Details Module. Aggregates data from previous modules, capturing expected vs. actual sell-out and dynamically calculating SOH (expected SOH). |  | Bilal |  | 25-07-25 |
| 5. |  | User access control: Brand, Customer, Category based |  | Bilal |  | 25-07-25 |
| KEY INITIATIVE #3: Data Security and Compliance |  |  |  |  |  |  |
| ITEM | WHAT |  | WHO |  | WHEN |  |
| 1. | Ensure compliance with relevant data protection standards and regulations throughout the project lifecycle. |  | Bilal |  | 05-06-25 |  |

| KEY INITIATIVE #4: Performance Monitoring and Reporting |  |  |  |
| --- | --- | --- | --- |
| ITEM | WHAT | WHO | WHEN |
| 1. | Define clear metrics for project success, including tracking accuracy, forecasting effectiveness, and customer data entry schedules. Implement regular performance monitoring and reporting. | AWA | N/A |

| Project requirements |  |  |  |
| --- | --- | --- | --- |
| ITEM | Subject | Current status | Remarks |
| 1. | SQL Server Integration | Tested | Existing MCSI database |
| 2. | Excel (PANDAS) Integration for Sell Out reports download and upload. | Tested | Development required |
| 3. | Python (Flask) for backend | Tested | Installed |
| 4. | Pandas Library | Tested | Installed |
| 5. | Secure data management tools | Tested | To ensure data protection compliance |

| Project Time lines |  |  |  |
| --- | --- | --- | --- |
| ITEM | Subject | ECD | Remarks |
| 1. | Modules development | July-2025 |  |
| 2. | All Module QA readiness | July-2025 |  |
| 3. | Domain/Hosting & security clearance | Aug-2025 | Subjected to AFG (will apply by end of July |
| 4. | Testing and bug fixes | Aug-2025 |  |
| 5. | User training | Aug-2025 |  |
| 6. | Production deployment | Aug-2025 |  |